## Instructions
ITC327W Phase 2 Project Progress Tracker
Use this workbook during Phase 2: System Architecture and Design. Update it throughout the phase and submit the same workbook with Assessment 2.
Sheet | Purpose | What must be kept current
Project Overview | Group details and automatic progress summary | Group information, GitHub link and current Phase 2 progress
Design Progress | Track each design artefact and supporting work | Architecture, UML, ERD, mobile/web interfaces, SRS and project-management tasks
Individual Contributions | Record work personally completed by each student | Activity, responsibility, work completed and evidence
Design Source Links | Record editable source links/files for submitted designs | Architecture, UML, ERD, mobile and web design sources
Challenges & Actions | Record design/project challenges and corrective action | Problem, effect, action, owner, target date and status
Phase Summary | Summarise what was achieved and what remains | Phase status, completed work, gaps and next priorities
Group Reflection | One shared group reflection for Phase 2 | Participation, collaboration, challenges, learning and improvements
Important
Do not create a separate tracker for each activity. This Phase 2 workbook is updated as the group progresses. Evidence may include GitHub commits, screenshots, document sections, editable design links/files and other appropriate project evidence. Do not include passwords, API keys or confidential stakeholder information.

## Project Overview
Phase 2 Project Overview
Group | Group D | Phase 2 Progress Summary
Project Title | Permission To Occupy (PTO) Management System | Total tracked items | 12
Stakeholder / Organisation | Mangaung Metropolitan Municipality Organisation | Completed | 12
Group Leader | Benny Hlungwane | In Progress | 0
Number of Group Members | 6 | Blocked | 0
GitHub Repository Link | https://github.com/HlungwaneB/PTO-Management-System.git | Average completion | 100%
Reporting Period | 13/10/2026
Overall Phase Status | Completed | Phase 2 Reminder
Phase 2 focuses on system architecture and design. Track the design artefacts, the editable source links/files, individual contributions, challenges, Microsoft Project updates and GitHub evidence. No separate stakeholder-evidence section is required in this tracker.

## Design Progress
Phase 2 Design Progress
Task ID | Design / Project Item | Description / Expected Output | Responsible Student(s) | Planned Date | Actual Completion Date | Status | % Complete | Evidence / Link | Notes / Action Required
P2-01 | System Architecture | Overall architecture showing Flutter, ASP.NET and shared Supabase backend | Benny & Bontle | 23/09/2026 | 24/09/2026 | Completed | 100% | https://drive.google.com/file/d/1WBh-Hiv2V74NSPv8v9fl7C-p25Q1AU0S/view?usp=sharing | Keep Supabase represented as backend, database, storage and authentication
P2-02 | Use Case Diagram | Actors, use cases, system boundary and appropriate UML relationships | Unarine, Bokamoso& Asive | 25/09/2026 | 2026-04-10 | Completed | 100% | https://drive.google.com/file/d/13mRYru-zK5hlS8O_3QRGihbv6UpAHD_3/view?usp=sharing | Check actor-to-use-case relationships against the updated requirements.
P2-03 | Sequence Diagram 1 | Important Flutter process | Unarine, Bokamoso& Asive | 26/09/2026 | 2026-04-10 | Completed | 100% | https://drive.google.com/file/d/1RCdWsGNttKu3tlA8mCnbEmuzx2rV7G06/view?usp=sharing | Administrator is not treated as a mobile-app user.
P2-04 | Sequence Diagram 2 | Important ASP.NET process | Unarine, Bokamoso& Asive | 27/09/2026 | 2026-04-10 | Completed | 100% | https://drive.google.com/file/d/1zymVeBIBddz3-NPUaYL9fXgwnM-0U4Tq/view?usp=sharing | All users are represented on the web side
P2-05 | ERD | Entities, attributes, PKs, FKs, relationships and cardinality | Bontle& Msawakhe | 26/09/2026 | 2026-04-10 | Completed | 100% | https://tinyurl.com/48anbe67 | Confirm ERD remains aligned with the final requirements.
P2-06 | Flutter Interface Designs | Main mobile screens and navigation | Benny& Msawakhe | 30/09/2026 | 2026-12-10 | Completed | 100% | https://www.figma.com/design/hF3g70wiKh3NJvoP6Dmpen/Untitled?node-id=0-1&p=f&t=jQzNewh1hYUo0MM9-0 | Ensure navigation reflects the approved mobile workflow.
P2-07 | ASP.NET Interface Designs | Main web pages and navigation | Benny & Msawakhe | 2026-01-10 | 2026-12-10 | Completed | 100% | https://www.figma.com/design/hF3g70wiKh3NJvoP6Dmpen/Untitled?node-id=0-1&p=f&t=jQzNewh1hYUo0MM9-0 | Ensure navigation the workflow of every user is represented
P2-08 | Design Alignment | Requirements linked across UML, ERD and interfaces |  | 2026-05-10 | 2026-09-10 | Completed |  |  | Maintain traceability during development
P2-09 | Updated SRS | Phase 2 architecture and design section inserted in existing SRS | Unarine&Bokamoso | 2026-01-10 | 2026-10-10 | Completed | 100% |  | Add the required appendices to the updated SRS
P2-10 | Microsoft Project | Schedule updated to reflect design progress and upcoming development | Bontle& Msawakhe | 2026-01-10 | 2026-12-10 | Completed | 100% | https://drive.google.com/file/d/1Uo5sqDHVdWggDIMcEA_ooj2hw8hdq9Bg/view?usp=sharing | Update actual progress and upcoming Phase 3 development tasks.
P2-11 | GitHub | Current design documentation and repository organisation | Benny | 30/09/2026 | 2026-09-10 | Completed | 100% | https://github.com/HlungwaneB/PTO-Management-System.git | Continue committing current design and development evidence.
P2-12 | Phase 2 Presentation | Presentation and defence preparation | Project Group | 2026-09-10 | 13/10/2026 | Completed | 100% |  | Finalise evidence, explanations and speaking roles before submission

## Individual Contributions
Phase 2 Individual Contributions
Student Name | Student Number | Activity / Artefact | Assigned Responsibility | Work Personally Completed | Date Completed | Hours Spent | Evidence / Link | Verified by Group | Verification Date | Quality / Review Notes | Contribution Status
Benny Hlungwane | 224022767 | GitHub repository and documentation | repository organisation | Record the repository, README, documentation structure and access checks personally completed. | 2026-11-10 | 3 hrs | https://github.com/HlungwaneB/PTO-Management-System.git | Yes | 2026-12-10 | Verify the repository contains the README and documentation folder and that the group has access. | Completed
Asive Mnyamanzi | 224113476 | Project tracking and coordination | Track The project progress | Record the task tracking, member follow-up and evidence coordination personally completed. | 2026-12-10 | 2 hrs |  | Yes | 13/10/2026 | Check that the tracker reflects actual progress. Record outstanding tasks, follow-ups and the evidence used to verify progress. | Completed
Bontle Mothudi | 224124772 | System architecture | System Architecture Design | Designed the overall system structure using Flutter, ASP.NET and Supabase. | 24/09/2026 | 4 hrs | https://drive.google.com/file/d/1WBh-Hiv2V74NSPv8v9fl7C-p25Q1AU0S/view?usp=sharing | Yes | 13/10/2026 | Review the system architecture to ensure Flutter and ASP.NET are correctly integrated with Supabase as the backend. | Completed
Bokamoso Luvhengo | 224015143 | Use Case diagram | Reviewing and refining diagram | Reviewed actor relationships and checked alignment with requirements | 2026-02-10 | 2 hrs | https://drive.google.com/file/d/13mRYru-zK5hlS8O_3QRGihbv6UpAHD_3/view?usp=sharing | Yes | 13/10/2026 | Confirm the diagram is readable, uses consistent UML notation and reflects the approved requirements. | Completed
Unarine Hangwani | 224073925 | Sequence diagrams | Review the and refining sequence diagrams | reviewed the sequences diagram and Supabase interactions. | 2026-02-10 | 3 hrs | https://drive.google.com/file/d/1tZK_eGJNWONjl7ZVAQ2BYRstlMcYC516/view?usp=sharing | Yes | 13/10/2026 | Review the two sequence diagrams for consistency and verify Supabase is represented as the backend for authentication, database and storage. Record any corrections. | Completed
Msawakhe Mlambo | 223059218 | Flutter interfaces | Design mobile app | Designed the main mobile application screens. | 2026-09-10 | 6 hrs | https://tinyurl.com/4ntknas4 | Yes | 13/10/2026 | Review the mobile screens to ensure they are user-friendly, easy to navigate and consistent with the PTO Management System requirements. Check that the screen layouts, input fields, buttons and navigation support the intended Beneficiary tasks. | Completed
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started

## Design Source Links
Phase 2 Original Design Source Links / Files
Design Artefact | Tool Used | Editable Link / File Name | Accessible to Lecturer? | Last Updated | Responsible Student | Included in SRS? | Notes
System Architecture | draw io | https://tinyurl.com/4db6yj2n | Yes | 24/09/2026 | Msawakhe,Benny, Bontle | Yes | Upload the latest architecture diagram and add a shareable editable/view link. Check that Flutter and ASP.NET connect to Supabase, which provides backend services, database, storage and authentication. Confirm lecturer access and whether it is included in the SRS.
Use Case Diagram | draw io | https://tinyurl.com/4ks4tbm2 | Yes | 2026-02-10 | Asive, Unarine, Bokamoso | Yes | Add the final use case diagram link. Check that Administrator, PTO Officer and Beneficiary are shown with the correct use cases, relationships and system boundary. Use the latest stakeholder-confirmed requirements and confirm lecturer access.
Sequence Diagram 1 | draw io | https://tinyurl.com/bdcnhxa4 | Yes | 2026-02-10 | Asive, Unarine, Bokamoso | Yes | Add the Flutter sequence diagram link. Check the order of messages, requests and responses, and show Supabase handling the relevant authentication/backend interactions. Do not show the Administrator as a mobile-app user.
Sequence Diagram 2 | draw io | https://tinyurl.com/4ntknas4 | Yes | 2026-02-10 | Asive, Unarine, Bokamoso | Yes | Add the ASP.NET sequence diagram link. Check the web workflow for Administrator and PTO applicants and ensure Supabase is shown as the backend. Verify message direction and return messages
ERD | draw io | https://tinyurl.com/48anbe67 | Yes | 2026-02-10 | Msawakhe,Benny, Bontle | Yes | Add the ERD link. Check entity names, attributes, primary and foreign keys, relationships and cardinalities.
Flutter Interface Designs | Figma | https://www.figma.com/design/hF3g70wiKh3NJvoP6Dmpen/Untitled?node-id=300-689&p=f&t=jQzNewh1hYUo0MM9-0 | Yes | 2026-09-10 | Msawakhe,Benny, Bontle | Yes | Add the Flutter interface design link or screenshot folder. Check that the mobile screens and navigation support the Beneficiary workflow and match the approved requirements. Ensure shared files can be viewed by the lecturer.
ASP.NET Interface Designs | Figma | https://www.figma.com/design/hF3g70wiKh3NJvoP6Dmpen/Untitled?node-id=0-1&p=f&t=jQzNewh1hYUo0MM9-0 | Yes | 2026-09-10 | Msawakhe | Yes | Add the ASP.NET interface design link or screenshot folder. Check that the web screens support Administrator and PTO Officer tasks and are consistent with the use case and sequence diagrams.
Navigation Flow | Figma (Prototypes) | https://www.figma.com/proto/hF3g70wiKh3NJvoP6Dmpen/Untitled?node-id=320-11925&p=f&t=ajQtHtzP4WYwDvLs-1&scaling=scale-down&content-scaling=fixed&page-id=300%3A689&starting-point-node-id=320%3A11925 | Yes | 13/10/2026 | Benny& Msawakhe | Yes | Add the navigation flow link. Check that the screen transitions match the Flutter and ASP.NET interfaces and that each role can reach only the relevant screens. Verify that the flow matches the final design.
https://www.figma.com/proto/hF3g70wiKh3NJvoP6Dmpen/Untitled?node-id=106-16&t=f7781PNJRa1UwXdE-1&scaling=scale-down&content-scaling=fixed&page-id=0%3A1&starting-point-node-id=106%3A3

## Challenges & Actions
Phase 2 Challenges and Corrective Actions
Date Identified | Challenge | Effect on Progress / Design | Corrective Action | Responsible Student | Target Date | Status | Resolved Date | Notes
17/09/2026 | Keeping requirements consistent after stakeholder feedback | Earlier requirements included actions that the stakeholder no longer wanted. | Consulted with our mentor and advised us to stick on the work that we presented on the previous phase | Group | 29/09/2026 | Completed | 30/09/2026 | Continue checking design artefacts against the confirmed requirements.
28/09/2026 | Diagrams weren't corresponding because everyone was doing them at the comfort of their own | This caused inconsistencies between the diagrams, required additional reviews and corrections, and delayed the finalisation of the Phase 2 design documentation. | The group reviewed the diagrams together, agreed on common requirements and design standards, and updated the diagrams to ensure consistency between the system architecture, use case diagram, sequence diagrams, ERD and class diagram. | Group | 2026-03-10 | Completed | 2026-12-10 | The group identified inconsistencies between the diagrams because members worked independently without a common design standard. The diagrams were reviewed and aligned with the agreed requirements to ensure consistency across the system. Future diagram updates will be discussed and reviewed collaboratively before finalisation.
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started

## Phase Summary
Phase 2 Progress Summary
Reporting Period | Phase 2 – System Architecture and Design | Phase 2 Completion Checklist | Complete?
Overall Phase Status | Completed | Architecture complete | Yes
What was completed during Phase 2? | The group developed the main Phase 2 design diagrams: system architecture, use case diagram, separate Flutter and ASP.NET sequence diagrams, ERD, mobile/web interface designs, updated SRS and GitHub documentation. | Use Case Diagram complete | Yes
What remains incomplete? | SRS document | Two Sequence Diagrams complete | Yes
Why is it incomplete? | Some evidence such as exact editable links, final Microsoft Project screenshots | ERD complete | Yes
Which contributions were particularly important? | Project management/GitHub organisation, requirements follow-up and UML/system-design work were important because they kept the Phase 2 diagrams aligned. | Flutter interfaces complete | Yes
Were there participation concerns? | No | ASP.NET interfaces complete | Yes
What will the group improve in Phase 3? | Improve early allocation of design tasks, keep evidence updated as work is completed, and review all diagrams before submission date. | Editable source links/files recorded | Yes
Main priority for Phase 3 | Finalise development planning, Microsoft Project updates, evidence links and Phase 3 implementations | SRS updated | Yes
|  | Microsoft Project updated | Yes
|  | GitHub current | Yes
|  | Individual contributions recorded | Yes
|  | Challenges/actions updated | Yes
|  | Group reflection completed | Yes

## Group Reflection
Phase 2 Group Reflection
1. What did the group complete successfully during Phase 2?
The group successfully produced the main Phase 2 architecture and design artefacts, including the system architecture, use case diagram, Flutter and ASP.NET sequence diagrams, ERD, interface designs, updated requirements/SRS content and GitHub documentation
2. Which architecture or design activities were the most challenging?
The most challenging activities were deciding how to represent Flutter, ASP.NET and Supabase clearly and separating mobile and web sequence processes also required careful consideration of which actors use each application.
3. How did the group ensure that Flutter, ASP.NET and Supabase were designed as one integrated system?
The group treated Flutter and ASP.NET as the application layers and Supabase as the shared backend responsible for authentication, database and storage. The architecture and sequence diagrams were adjusted to reflect this integration
4. How was work divided among group members, and was participation balanced?
Work was divided according to the group's assigned responsibilities, with members contributing to requirements, diagrams, interfaces, documentation and project management. Participation was checked against the individual contribution and evidence records before final submission.
5. What did the group learn from developing the UML, ERD and interface designs?
The group learnt that UML, ERD and interface designs must describe the same system consistently. Changes to a requirement can affect several diagrams and screens, so the designs need to be reviewed together rather than independently.
6. What will the group do differently during development in Phase 3?
As a group we decided that we will have meetings frequently to avoid the diagrams that aren't corresponding and we will allocate development tasks more explicitly, maintain GitHub evidence continuously, update Microsoft Project as work happens, test integrations early and keep checking implementation against the approved requirements and designs.